## Summary
SOUND FOR SILENCE - TESTING SUMMARY
Section | Total Items | Passed ✅ | Failed ❌ | Pending 🔄 | % Complete
A1. Parent - Auth & Home | 47 | 0 | 0 | 47 | 0%
A2. Parent - Videos & Player | 54 | 0 | 0 | 54 | 0%
A3. Parent - Quiz, Progress, Settings | 58 | 0 | 0 | 58 | 0%
B. Therapist Panel | 37 | 0 | 0 | 37 | 0%
C. Admin Panel | 77 | 0 | 0 | 77 | 0%
D. Backend & Security | 45 | 0 | 0 | 45 | 0%
E-G. Logic, Integration, Edge Cases | 52 | 0 | 0 | 52 | 0%
TOTAL | 370 | 0 | 0 | 370 | 0%
SIGN-OFF
Role | Name | Date | Signature
Developer
QA Tester
Project Lead
Client (AIIMS)
⭐ = Critical/Priority test case
Document Version: 1.0 ¦ Based on: Sound for Silence Project Specification v1.0

## A1-Parent Auth & Home
PART A: PARENT MOBILE APP (Android)
# | Test Case | Status | Notes/Issues | Tested By
A1.1 Registration
1 | User can access registration screen from login | DEVELOPED | Yes
2 | Registration form has: Name field | IN-PROGRESS | Yes, I guess only Text should be allowed, Currently no.s are allowed in name field
3 | Registration form has: Mobile number field | DEVELOPED | Yes
4 | Registration form has: Password field | DEVELOPED | Yes
5 | Registration form has: Child name field | IN-PROGRESS | Yes, same issue....can type no.s in this field
6 | Registration form has: Child date of birth field | DEVELOPED | Yes
7 | Registration form has: Implant date field | PENDING | Yes, Implant date cannot be later than Child birth date
8 | Language selection available at registration (Hindi/English) | IN-PROGRESS | No
9 | Mobile number validation (10 digits, Indian format) | DEVELOPED | Yes
10 | Password minimum requirements enforced | IN-PROGRESS | Yes 6
11 | Duplicate mobile number shows appropriate error | IN-PROGRESS | Yes
12 | Successful registration redirects to home screen | IN-PROGRESS | Yes
13 | Registration works offline with sync later | IN-PROGRESS | No, currently requires internet to register
A1.2 Login
1 | Login screen displays mobile number field | 🔄 Pending | Yes
2 | Login screen displays password field | 🔄 Pending | Yes
3 | Login button is clearly visible and tappable | 🔄 Pending | Yes
4 | Invalid credentials show appropriate error message | 🔄 Pending | Yes
5 | Successful login redirects to home screen | 🔄 Pending | Yes
6 | ⭐ PERSISTENT LOGIN: User stays logged in after app close | 🔄 Pending | Yes, login screen shows for a sec when app is reopen after login then get redirects properly
7 | ⭐ PERSISTENT LOGIN: User stays logged in after phone restart | 🔄 Pending | Yes
8 | User remains logged in until manual logout | 🔄 Pending | Yes
9 | Login works with poor network (shows loading state) | 🔄 Pending | Yes, works with poor network - Tested for Network Limit 128kbps
A1.3 Logout
1 | Logout option available in Settings | 🔄 Pending | Yes
2 | Logout confirmation prompt appears | 🔄 Pending | No
3 | After logout, user is redirected to login screen | 🔄 Pending | Yes
4 | After logout, protected screens are inaccessible | 🔄 Pending | Yes
5 | Downloaded videos remain after logout (or cleared based on design) | 🔄 Pending | Yes
A2.1 Home Screen - Welcome & Overview
1 | Welcome message displays parent's name | 🔄 Pending | Yes
2 | Welcome message displays child's name | 🔄 Pending | Yes
3 | Overall progress statistic shown (videos completed) | 🔄 Pending | No, currently shows total videos
4 | Overall progress percentage displayed | 🔄 Pending | Yes
5 | Home screen loads within 3 seconds | 🔄 Pending | Yes
A2.2 Home Screen - Category List Display
1 | All active categories are displayed | 🔄 Pending | Yes
2 | Categories displayed in correct order (as set by admin) | 🔄 Pending | Yes
3 | Each category shows name (in selected language) | 🔄 Pending | No
4 | Each category shows progress: "X of Y videos completed" | 🔄 Pending | Yes
5 | Category cards are tappable | 🔄 Pending | Yes
6 | Tapping category navigates to video list | 🔄 Pending | Yes
7 | Subcategories display correctly under parent category | 🔄 Pending | Yes, should be a title present above the video list
8 | Empty categories handled gracefully | 🔄 Pending | No message is shown
A2.3 Bottom Navigation
1 | Bottom navigation bar is visible | 🔄 Pending | Yes
2 | "Home" tab present and functional | 🔄 Pending | Yes
3 | "Progress" (CAP/SIR Scores) tab present and functional | 🔄 Pending | Yes
4 | "Settings" tab present and functional | 🔄 Pending | Yes
5 | Active tab is visually highlighted | 🔄 Pending | Yes
6 | Navigation persists across screens | 🔄 Pending | Yes

## A2-Parent Videos
PARENT APP: Category & Video Features
# | Test Case | Status | Notes/Issues | Tested By
A3.1 Category Screen
1 | Category title displayed at top | In Progress | No
2 | Back button to return to home | In Progress | Yes
3 | All videos in category are listed | In Progress | Yes
4 | Videos displayed in correct order (position) | In Progress | Yes
5 | Subcategory videos grouped correctly | In Progress | No Subcategories
A3.2 Video List Item Display
1 | Video thumbnail displayed | Pending | No
2 | Video title displayed (in selected language) | Pending | Title Displayed, but not in selected language
3 | Video duration displayed | In Progress | Yes
4 | Progress percentage shown for in-progress videos | In Progress | Yes
A3.3 Video Status Indicators
1 | COMPLETED videos show checkmark (✓) | Pending | Yes
2 | IN PROGRESS videos show percentage (%) | In Progress | Yes
3 | LOCKED videos show lock icon (🔒) | Pending | Yes
4 | UNLOCKED but not started videos show play icon | Pending | Yes
5 | Visual distinction clear between all states | Pending | Yes
⭐ A3.4 Sequential Unlocking Logic (CRITICAL)
1 | ⭐ First video in category is ALWAYS unlocked | Pending | Yes
2 | Video 2 is locked until Video 1 is complete | Pending | Yes, Videos can be skipped and completed
3 | Video N+1 unlocks only after Video N completion | Pending | Yes
4 | Tapping locked video shows appropriate message | Pending | No message is shown
5 | Unlocking works correctly across app restarts | Pending | Yes
6 | Progress syncs correctly after offline use | Pending | Offline Use Not available
A3.5 Download Functionality
1 | Download button visible for each video | Pending | Yes
2 | Download progress indicator shown during download | Pending | No
3 | Downloaded videos show "Downloaded" indicator | Pending | Yes
4 | Download works on Wi-Fi | Pending | Yes
5 | Download works on mobile data (with confirmation) | Pending | Yes, no confirmation
6 | Partial downloads can be resumed | Pending | No
7 | Download failure shows appropriate error | Pending | No
8 | User can delete downloaded videos | Pending | Yes
A4.1 Video Player - Basic Playback
1 | Video plays when tapped | Pending | Yes
2 | Large, simple play/pause button visible | Pending | Partially Visible
3 | Play/pause button is easily tappable | Pending | No
4 | Progress bar showing watched percentage | Pending | Yes
5 | Video title displayed on player screen | Pending | Yes
6 | Back button to return to video list | Pending | Yes
⭐ A4.2 Video Player - Progress Tracking (CRITICAL)
1 | ⭐ Progress saved if user exits mid-video | Pending | No
2 | ⭐ Resume from last position on return | Pending | No
3 | Progress bar reflects actual watched position | Pending | Yes
4 | Seeking forward/backward works | Pending | Yes
5 | Progress syncs to server when online | Pending | Offline Use Not available
6 | 100% completion marks video as complete | Pending | Sometimes shows less than 100% even after completing 100% of Video
⭐ A4.3 Offline Playback (CRITICAL)
1 | ⭐ Downloaded videos play without internet | 🔄 Pending | No
2 | Offline playback quality is acceptable | 🔄 Pending | No
3 | Progress tracked during offline playback | 🔄 Pending | No
4 | Progress syncs when back online | 🔄 Pending | No
5 | Non-downloaded videos show "Download required" when offline | 🔄 Pending | No
⭐ A4.4 DRM Protection (CRITICAL)
1 | ⭐ Videos encrypted on device | 🔄 Pending | Yes
2 | ⭐ Videos playable ONLY within app | 🔄 Pending | Yes
3 | Videos NOT accessible via file manager | 🔄 Pending | Yes
4 | Videos CANNOT be shared via WhatsApp | 🔄 Pending | Yes
5 | Videos CANNOT be shared via any other app | 🔄 Pending | Yes
6 | Screen recording blocked (if implemented) | 🔄 Pending | Yes, blocked at the time of Video playing
A4.5 Streaming (Online Playback)
1 | Video streams without downloading first | 🔄 Pending | Yes
2 | Adaptive quality based on network speed | 🔄 Pending | Yes
3 | Buffering indicator shown when loading | 🔄 Pending | Yes
4 | Graceful handling of network interruption | 🔄 Pending | No

## A3-Parent Quiz & Progress
PARENT APP: Quiz, Progress & Settings
# | Test Case | Status | Notes/Issues | Tested By
A5.1 Post-Video Questions - Display
1 | Questions appear AFTER video completion (100%) | 🔄 Pending | Yes
2 | Question text displayed clearly (in selected language) | 🔄 Pending | No
3 | Multiple choice options displayed | 🔄 Pending | Yes
4 | Options are easily tappable | 🔄 Pending | Yes
5 | Only one option selectable at a time | 🔄 Pending | Yes
⭐ A5.2 Skip Functionality (CRITICAL)
1 | ⭐ Skip button is clearly visible | 🔄 Pending | Yes
2 | ⭐ Skipping marks video as complete | 🔄 Pending | Yes
3 | ⭐ Skipping unlocks next video | 🔄 Pending | Yes
4 | Skip action recorded in database | 🔄 Pending
A5.3 Correct Answer Flow
1 | Correct answer shows success feedback | 🔄 Pending | Yes
2 | Next video unlocks after correct answer | 🔄 Pending | Yes
3 | Answer recorded in database | 🔄 Pending
⭐ A5.4 Wrong Answer Flow (CRITICAL)
1 | Wrong answer shows feedback | 🔄 Pending | Yes
2 | ⭐ Two options presented after wrong answer: | 🔄 Pending | No
3 | - Option A: "Re-watch video and try again" | 🔄 Pending | No
4 | - Option B: "Consult Speech Therapist" (WhatsApp) | 🔄 Pending | No
5 | ⭐ User can STILL proceed to next video (NOT BLOCKED) | 🔄 Pending | Yes
6 | Re-watch option takes user back to video | 🔄 Pending
A5.5 WhatsApp Integration
1 | "Consult Therapist" opens WhatsApp | 🔄 Pending | No
2 | WhatsApp opens with correct therapist number | 🔄 Pending | No
3 | ⭐ Pre-filled message includes: Question text | 🔄 Pending | No
4 | ⭐ Pre-filled message includes: Child name | 🔄 Pending | No
5 | ⭐ Pre-filled message includes: Video reference | 🔄 Pending | No
6 | Works if WhatsApp is installed | 🔄 Pending | No
7 | Shows appropriate message if WhatsApp not installed | 🔄 Pending | No
A6.1 Progress Screen - CAP/SIR Score Display
1 | Progress screen accessible from bottom navigation | 🔄 Pending | Yes
2 | Child's name displayed on screen | 🔄 Pending | No
3 | CAP scores displayed for all assessed periods | 🔄 Pending | Yes
4 | SIR scores displayed for all assessed periods | 🔄 Pending | Yes
5 | Scores shown at milestones: 3, 6, 9, 12, 18, 24 months | 🔄 Pending | Yes, upto 12 months available in Therapist panel
6 | Visual representation of progress over time (chart/graph) | 🔄 Pending | No
7 | Chart is easy to understand | 🔄 Pending | No
8 | Empty state shown if no assessments yet | 🔄 Pending | Yes
9 | Next assessment due date shown | 🔄 Pending | No
10 | Due date calculated correctly from implant date | 🔄 Pending | No
A7.1 Settings - Language
1 | Language switch option available | 🔄 Pending | Yes
2 | Can switch between Hindi and English | 🔄 Pending | Yes
3 | ⭐ UI changes to selected language | 🔄 Pending | Yes, Not all e.g. Video section Title
4 | ⭐ Videos remain in Hindi regardless of UI language | 🔄 Pending
5 | Language preference persists after app restart | 🔄 Pending | NO
A7.2 Settings - Profile & Child
1 | View current profile information | 🔄 Pending | Yes
2 | Edit parent name | 🔄 Pending | Yes
3 | Edit mobile number | 🔄 Pending | No, If parent registered from Admin Panel There are two No.s - Phone No. and Login ID Mobile No. We cannot change Login Id Mobile no.
4 | Save changes with confirmation | 🔄 Pending | No, If parent registered from Admin Panel
5 | View child details | 🔄 Pending | Yes, But should show Age in Years and months
6 | Edit child name | 🔄 Pending | Yes
7 | View implant date | 🔄 Pending | No
A7.3 Settings - Downloads & Others
1 | View list of downloaded videos | 🔄 Pending | Yes
2 | View total storage used | 🔄 Pending | No
3 | Delete individual downloaded videos | 🔄 Pending | Yes
4 | Delete all downloaded videos option | 🔄 Pending | No
5 | Notification preferences accessible | 🔄 Pending | Yes
6 | Help & FAQ section accessible | 🔄 Pending | No
7 | FAQs in selected language | 🔄 Pending | No
8 | Logout option visible and works | 🔄 Pending | Yes
⭐ A8 UI/UX - Simplicity Requirements (CRITICAL)
1 | ⭐ "Grandmother test": Interface simple for elderly non-tech user | 🔄 Pending
2 | Large, easily tappable buttons (min 48dp) | 🔄 Pending | Yes
3 | Minimal text, more visual indicators | 🔄 Pending | Yes
4 | Clear visual hierarchy | 🔄 Pending | Yes
5 | Consistent navigation patterns | 🔄 Pending | Yes
6 | No complex gestures required | 🔄 Pending | Yes
7 | Error messages in simple, non-technical language | 🔄 Pending | Yes
8 | Text size readable | 🔄 Pending | Yes
9 | Sufficient color contrast | 🔄 Pending
10 | Works on low-end Android phones | 🔄 Pending
11 | Small app size (APK) | 🔄 Pending | Yes
12 | Low data usage for streaming | 🔄 Pending
13 | No crashes during normal use | 🔄 Pending | No Crashes

## B-Therapist Panel
PART B: THERAPIST WEB PANEL
# | Test Case | Status | Notes/Issues | Tested By
B1. Authentication
1 | Login page accessible | 🔄 Pending | Yes
2 | Login with valid credentials works | 🔄 Pending | Yes
3 | Invalid credentials show error | 🔄 Pending | Yes
4 | Session management works correctly | 🔄 Pending
5 | Logout functionality works | 🔄 Pending | Yes
B2. Dashboard
1 | Dashboard loads after login | 🔄 Pending | Yes
2 | List of assigned patients (children) displayed | 🔄 Pending | Yes
3 | Patient name visible in list | 🔄 Pending | Yes
4 | Parent name visible in list | 🔄 Pending | Yes
5 | Assessment status for each patient shown | 🔄 Pending | Yes
6 | Last assessment date visible | 🔄 Pending | No
7 | Next due assessment visible | 🔄 Pending | Yes
8 | Quick access button to add new assessment | 🔄 Pending | Yes
9 | Search/filter patients functionality | 🔄 Pending | Yes
B3. Assessment Entry - Patient Selection
1 | Can select patient from assigned list | 🔄 Pending | Yes
2 | Only assigned patients visible | 🔄 Pending | Yes
3 | Patient details visible on selection | 🔄 Pending | No
⭐ B3. Assessment Entry - Form (CRITICAL)
1 | Assessment period dropdown available | 🔄 Pending | Yes
2 | Periods: 3, 6, 9, 12, 18, 24 months available | 🔄 Pending | 18, 24 are missing
3 | ⭐ CAP score input field (0-7) | 🔄 Pending | Yes
4 | ⭐ CAP score validation (only 0-7 accepted) | 🔄 Pending | Yes, UI Needs to be improved
5 | ⭐ SIR score input field (0-5) | 🔄 Pending | Yes
6 | ⭐ SIR score validation (only 0-5 accepted) | 🔄 Pending | Yes, UI Needs to be improved
7 | Optional notes/observations field | 🔄 Pending | Yes
8 | Save button clearly visible | 🔄 Pending | Yes
9 | Save confirmation shown | 🔄 Pending | Yes
10 | ⭐ Saved scores appear in parent app | 🔄 Pending | Yes
B3. Assessment Entry - Validation
1 | Cannot save without selecting patient | 🔄 Pending | Yes
2 | Cannot save without selecting period | 🔄 Pending | Yes
3 | Cannot save without CAP score | 🔄 Pending | Yes
4 | Cannot save without SIR score | 🔄 Pending | Yes
5 | Duplicate period for same patient handled | 🔄 Pending | No
B4. Patient History
1 | Can view all historical scores for a patient | 🔄 Pending | Yes
2 | Scores listed chronologically | 🔄 Pending | No
3 | CAP and SIR scores visible for each entry | 🔄 Pending | Yes
4 | Assessment date visible | 🔄 Pending | Yes
5 | Notes visible for each entry | 🔄 Pending | No
6 | Visual progress chart displayed | 🔄 Pending | No
7 | Chart shows CAP progression | 🔄 Pending | NO
8 | Chart shows SIR progression | 🔄 Pending | No
9 | Can edit previous entries | 🔄 Pending | No
10 | Edit confirmation required | 🔄 Pending | No

## C-Admin Panel
PART C: ADMIN WEB PANEL
# | Test Case | Status | Notes/Issues | Tested By
C1. Authentication & Access
1 | Login page accessible | 🔄 Pending | Yes
2 | Admin login works with valid credentials | 🔄 Pending | Yes
3 | Invalid credentials rejected | 🔄 Pending | Yes
4 | Superadmin login works | 🔄 Pending | Yes
5 | Role-based access enforced | 🔄 Pending | No
6 | Logout functionality works | 🔄 Pending | Yes
C2. Dashboard & Analytics
1 | Dashboard loads after login | 🔄 Pending | Yes
2 | Total categories count displayed | 🔄 Pending | Yes
3 | Total videos count displayed | 🔄 Pending | Yes
4 | Active parents count displayed | 🔄 Pending | Yes
5 | Total video views displayed | 🔄 Pending | Yes, but no data
6 | Category-wise engagement statistics | 🔄 Pending | No
7 | Recent activity log displayed | 🔄 Pending | Yes, Not sure if working correctly
8 | Analytics data is accurate | 🔄 Pending | Not all
9 | Dashboard refreshes/updates | 🔄 Pending | Yes
C3. Category Management - View & Create
1 | List of all categories displayed | 🔄 Pending | Yes
2 | Category name (Hindi) visible | 🔄 Pending | No
3 | Category name (English) visible | 🔄 Pending | Yes
4 | Category position/order visible | 🔄 Pending | Yes
5 | Active/inactive status visible | 🔄 Pending | Yes
6 | Video count per category visible | 🔄 Pending | Yes
7 | "Create Category" button accessible | 🔄 Pending | Yes
8 | Form has Hindi name field | 🔄 Pending | No
9 | Form has English name field | 🔄 Pending | Yes
10 | Form has description field | 🔄 Pending | No
11 | Form has position field | 🔄 Pending | Yes
12 | Can create as subcategory | 🔄 Pending | No
13 | Save creates category successfully | 🔄 Pending | Yes
14 | New category appears in parent app | 🔄 Pending | Yes, but dosen't disappear after changed to inactive
C3. Category Management - Edit, Delete, Reorder
1 | Edit button accessible for each category | 🔄 Pending | Yes
2 | Edit form pre-fills existing data | 🔄 Pending | Yes
3 | Can edit all fields | 🔄 Pending | Yes
4 | Changes reflected in parent app | 🔄 Pending | Not active/inactive status, rest working
5 | Delete button accessible | 🔄 Pending | Yes
6 | ⭐ Confirmation prompt before delete | 🔄 Pending | Yes
7 | Deletion removes category from parent app | 🔄 Pending | Yes
8 | Drag-drop reordering works | 🔄 Pending | No, ordering is done by numbering which works but other category numbers does not adjust according to changes
9 | New order reflected in parent app | 🔄 Pending | Yes
C4. Video Management - View & Upload
1 | List of all videos displayed | 🔄 Pending | Yes
2 | Filter by category works | 🔄 Pending
3 | Video title, duration, category visible | 🔄 Pending | Duration & Views not visible, Rest Visible
4 | "Upload Video" button accessible | 🔄 Pending | Upload video button visible, when clicks should automatically scrolled down to bottom section (which shows video upload details)
5 | File upload field works | 🔄 Pending | Sometimes No
6 | Supported formats accepted (MP4) | 🔄 Pending | Yes
7 | Upload progress indicator shown | 🔄 Pending | No
8 | Large file upload works | 🔄 Pending | No
9 | Title (Hindi + English) fields | 🔄 Pending | Yes, But dosen't work in Parent's App
10 | Description field | 🔄 Pending | Yes, No hindi
11 | Category selection dropdown | 🔄 Pending | Yes
12 | Position selection | 🔄 Pending | Yes
13 | Thumbnail auto-generated or uploadable | 🔄 Pending | No thumbnail is visible in parents apk nor there is an option to upload
14 | Save uploads video successfully | 🔄 Pending | Yes
15 | Video appears in parent app | 🔄 Pending | Yes
C4. Video Management - Questions
1 | "Add Questions" option available | 🔄 Pending | Yes, After the video is uploaded
2 | Question text field (Hindi) | 🔄 Pending | No
3 | Question text field (English) | 🔄 Pending | Yes
4 | Multiple choice options input | 🔄 Pending | Yes
5 | Correct option selection | 🔄 Pending | Yes
6 | Can add multiple questions per video | 🔄 Pending | Yes
7 | Questions appear in parent app after video | 🔄 Pending | Yes
C4. Video Management - Edit, Delete, Reorder
1 | Edit button accessible for each video | 🔄 Pending | Yes
2 | Can edit title, description, category, position | 🔄 Pending | Yes
3 | Can edit/add/remove questions | 🔄 Pending | Yes
4 | Can replace video file | 🔄 Pending | Needs to be check
5 | Changes reflected in parent app | 🔄 Pending | Yes
6 | Delete button accessible | 🔄 Pending | Yes
7 | ⭐ Confirmation prompt before delete | 🔄 Pending | Yes
8 | Deletion removes video from parent app | 🔄 Pending | Yes
9 | Reorder videos within category works | 🔄 Pending | Yes
10 | New order reflected in parent app | 🔄 Pending | Yes
11 | Sequential unlocking respects new order | 🔄 Pending | No
C5. User Management
1 | View all parents | 🔄 Pending | No, When parents register from android apk the profile are visible in admin panel
2 | Search parents by name/mobile | 🔄 Pending | No , Search option is not available
3 | Add/Edit/Delete parent | 🔄 Pending | When parents are added via admin panel ,the details of profile is not shown in android apk when logged in not editable and when deleted the account doesn't get logged out in the android apk
4 | View parent's progress | 🔄 Pending | No
5 | View all therapists | 🔄 Pending | Yes
6 | Add/Edit/Delete therapist | 🔄 Pending | Addition is working edit and delete is not working
7 | Assign patients to therapist | 🔄 Pending | Yes
8 | (Superadmin) View/Add/Edit/Delete admins | 🔄 Pending | Not working , no login credential were given
9 | (Superadmin) Assign roles to admins | 🔄 Pending | Not working
10 | ⭐ Can set therapist WhatsApp number for each child | 🔄 Pending | No
11 | WhatsApp number validated | 🔄 Pending | No
12 | Number used in parent app "Consult Therapist" | 🔄 Pending | No
C6. Role & Permission Management (Superadmin Only)
1 | Only superadmin can access | 🔄 Pending | Yes
2 | View all roles | 🔄 Pending | Yes , analytics is missing
3 | Create new custom role | 🔄 Pending | Not working
4 | Edit/Delete role | 🔄 Pending | No
5 | Assign/revoke "Upload videos" permission | 🔄 Pending | No
6 | Assign/revoke "Manage categories" permission | 🔄 Pending | No
7 | Assign/revoke "Manage users" permission | 🔄 Pending | No
8 | Assign/revoke "View analytics" permission | 🔄 Pending | No
9 | Permission changes take effect immediately | 🔄 Pending | No
10 | Admin without permission cannot access feature | 🔄 Pending | No

## D-Backend & Security
PART D: BACKEND, API & SECURITY
# | Test Case | Status | Notes/Issues | Tested By
D1. Authentication APIs
1 | POST /api/auth/register works | 🔄 Pending
2 | POST /api/auth/login returns JWT | 🔄 Pending
3 | POST /api/auth/logout invalidates session | 🔄 Pending
4 | POST /api/auth/refresh-token works | 🔄 Pending
5 | POST /api/auth/forgot-password works | 🔄 Pending
6 | Invalid credentials return 401 | 🔄 Pending
7 | Missing fields return 400 | 🔄 Pending
D2. Parent App APIs
1 | GET /api/categories returns all categories with progress | 🔄 Pending
2 | GET /api/categories/:id/videos returns videos | 🔄 Pending
3 | GET /api/videos/:id returns video details | 🔄 Pending
4 | GET /api/videos/:id/stream works (HLS) | 🔄 Pending
5 | GET /api/videos/:id/download works | 🔄 Pending
6 | POST /api/progress/video updates progress | 🔄 Pending
7 | GET /api/progress/overview returns stats | 🔄 Pending
8 | GET /api/videos/:id/questions returns questions | 🔄 Pending
9 | POST /api/questions/:id/answer records answer | 🔄 Pending
10 | GET /api/child/scores returns CAP/SIR scores | 🔄 Pending
11 | GET /api/profile returns user profile | 🔄 Pending
12 | PUT /api/profile updates profile | 🔄 Pending
13 | PUT /api/settings/language changes language | 🔄 Pending
D3. Therapist & Admin APIs
1 | GET /api/therapist/patients returns assigned patients | 🔄 Pending
2 | POST /api/therapist/scores adds new score | 🔄 Pending
3 | PUT /api/therapist/scores/:id edits score | 🔄 Pending
4 | Therapist cannot access unassigned patients | 🔄 Pending
5 | GET /api/admin/dashboard returns analytics | 🔄 Pending
6 | Category CRUD endpoints work | 🔄 Pending
7 | Video CRUD endpoints work | 🔄 Pending
8 | User CRUD endpoints work | 🔄 Pending
9 | Role/Permission endpoints work (superadmin only) | 🔄 Pending
⭐ D4. Security Testing (CRITICAL)
1 | JWT expiry enforced | 🔄 Pending
2 | Invalid JWT rejected with 401 | 🔄 Pending
3 | Role-based access control (RBAC) enforced | 🔄 Pending
4 | SQL injection attempts blocked | 🔄 Pending
5 | XSS attempts sanitized | 🔄 Pending
6 | HTTPS enforced for all communications | 🔄 Pending
7 | Input validation on all fields | 🔄 Pending
8 | Rate limiting implemented | 🔄 Pending
9 | Password hashing secure (bcrypt/similar) | 🔄 Pending
D5. Video Infrastructure
1 | Videos stored in cloud (S3/GCS) | 🔄 Pending
2 | CDN configured for fast delivery | 🔄 Pending
3 | HLS streaming works | 🔄 Pending
4 | Multiple quality options (360p, 480p, 720p) | 🔄 Pending
5 | Adaptive streaming based on network | 🔄 Pending
6 | ⭐ DRM (Widevine) protection active | 🔄 Pending
7 | Videos compressed for low bandwidth | 🔄 Pending

## E-Logic & Integration
PART E: BUSINESS LOGIC & INTEGRATION
# | Test Case | Status | Notes/Issues | Tested By
⭐ E1. Video Unlocking Logic (CRITICAL)
1 | ⭐ First video in category is ALWAYS unlocked | 🔄 Pending | Yes
2 | Video marked complete at 100% watched | 🔄 Pending | yes, progress % sometime incorrect
3 | Video N+1 unlocks only after Video N complete | 🔄 Pending | Yes
4 | ⭐ Questions do NOT affect unlocking | 🔄 Pending
5 | ⭐ Skipping questions still unlocks next video | 🔄 Pending | Yes
6 | ⭐ Wrong answer does NOT block next video | 🔄 Pending | Yes
7 | Unlocking persists after app restart | 🔄 Pending | Yes
8 | Unlocking syncs correctly after offline use | 🔄 Pending | No offline use available
⭐ E2. CAP/SIR Score Logic (CRITICAL)
1 | CAP score accepts only 0-7 | 🔄 Pending | Yes
2 | SIR score accepts only 0-5 | 🔄 Pending | yes
3 | Milestones: 3, 6, 9, 12, 18, 24 months only | 🔄 Pending | 18 and 24 are missing
4 | Milestone calculated from implant date | 🔄 Pending | No ,
5 | Only assigned therapist can enter scores | 🔄 Pending | Yes
6 | ⭐ Scores visible to parent in app | 🔄 Pending | Yes
7 | Historical scores preserved | 🔄 Pending
⭐ E3. Offline Video Rules (CRITICAL)
1 | Downloaded videos encrypted | 🔄 Pending | No
2 | ⭐ Videos playable ONLY within app | 🔄 Pending | Yes
3 | Cannot share via any method | 🔄 Pending | Yes
4 | Progress stored locally when offline | 🔄 Pending | No
5 | Progress syncs when online | 🔄 Pending | No
6 | Video expiry works (if implemented) | 🔄 Pending
E4. WhatsApp Integration Logic
1 | Correct therapist WhatsApp number used | 🔄 Pending | No
2 | Pre-filled message includes question text | 🔄 Pending | No
3 | Pre-filled message includes child name | 🔄 Pending | No
4 | Pre-filled message includes video reference | 🔄 Pending | No
5 | Opens WhatsApp app correctly | 🔄 Pending | No
F1. End-to-End Integration Flows
1 | Admin uploads video → Parent sees video | 🔄 Pending | Yes
2 | Admin creates category → Parent sees category | 🔄 Pending | Yes
3 | Admin reorders categories → Parent sees new order | 🔄 Pending | Yes
4 | Therapist enters score → Parent sees score | 🔄 Pending | Yes
5 | Admin assigns therapist → Therapist sees child | 🔄 Pending | Yes
6 | Admin sets WhatsApp number → Parent "Consult" uses it | 🔄 Pending | No
7 | Parent watches video → Progress in admin analytics | 🔄 Pending | No
F2. Data Sync
1 | Progress syncs from offline to online | 🔄 Pending | No
2 | New content syncs to app (pull refresh) | 🔄 Pending | Yes
3 | Deleted content removes from app | 🔄 Pending | Yes
G1. Network & Edge Cases
1 | App handles no internet gracefully | 🔄 Pending | No
2 | App handles slow internet | 🔄 Pending | Yes
3 | App handles network timeout | 🔄 Pending
4 | App handles interrupted video stream | 🔄 Pending | Yes
5 | Offline mode works completely | 🔄 Pending | Does not work
6 | Empty categories handled | 🔄 Pending | No
7 | No videos in category message | 🔄 Pending | No
8 | No assessments yet message | 🔄 Pending | Yes
9 | Hindi unicode characters display correctly | 🔄 Pending | No
G2. Device Compatibility
1 | Works on Android 8.0+ | 🔄 Pending
2 | Works on low-end devices (1GB RAM) | 🔄 Pending
3 | Works on various screen sizes | 🔄 Pending
4 | Web panels work on Chrome | 🔄 Pending
5 | Web panels work on Firefox | 🔄 Pending
6 | Web panels work on Safari | 🔄 Pending
7 | Web panels work on mobile browsers | 🔄 Pending

## Notes
Notes
When Parent registration is done via Android APK - No addition in Admin Panel Database
When Parent registration is done via Admin Panel - Name of the parent is different (Abhishek Ji), Maybe the therapistname is coming? Also cannot change Login ID Mobile no. from Andriod APK and shows Firebase error
Hindi and English laguage Needs to be properly changed for every data
Where can we check Quiz scores?
Next due - should be date in Therapist portal...
Add admin and add role (permissions) are not working properly - Admin registration issue ,
Please check recent activity logs - How much past data needs to be stored/discussed
Do we need day streak statistics in the android apk ? - need to be discussed
Need access to quiz score in android apk
Colour - Theme of android apk needs to be improved